## Sheet1
Project: Problem 5 - Appointment Level 3 Backlog
Members: | Lilou, Yipeng Liu, Zhuying
Task | Description | Priority | Member | Status | Start Date | Complete Date | Comments
GitHub | Setting up github repository | 1 | All | Completed | 2021-07-15 | 2021-07-15 | All done.
Brainstorm Meeting | Video meeting to discuss about the project | 1 | All | Completed | 2021-07-24 | 2021-07-24 | 19:00
Create GUI (base file) |  | 2 | All | Completed | 2021-07-29 | 2021-07-29
Set Up GUI | Writing the code of buttons |  |  | Waiting
Modify print | Bullet point 1 | 2 | Lilou | Completed | 2021-07-26 | 2021-07-26
Method print && Occur on | Bullet point 2 | 2 | Zhuying | Not Started
Method Save appointment | Bullet point 3 | 2 | Yipeng Liu | In Progress | 2021-07-30
Load file | Bullet point 4 | 2 | Yipeng Liu | In Progress | 2021-07-30
Record Keeping | Keeping meeting minutes | 4 | Yipeng Liu | In Progress | 2021-07-24
Meeting | Meeting for backend functionality (level 2) | 1 | All | Waiting |  |  | 07/31 PT 18:00

## Utils (hidden)
Priority | Status | Member | All | Lilou | Yipeng Liu | Zhuying
1 | Waiting
2 | Not Started
3 | In Progress
4 | Completed