## Sheet1
Members: | Lilou, Yipeng Liu, Zhuying
Task | Description | Priority | Member | Status | Start Date | Complete Date | Comments
GitHub | Setting up github repository | 1 | All | Completed | 2021-07-15 | 2021-07-15 | All done.
Brainstorm Meeting | Video meeting to discuss about the project | 1 | All | Completed | 2021-07-24 | 2021-07-24 | 19:00
Create GUI (base file) |  | 2 | All | Completed | 2021-07-29 | 2021-07-29
Modify print | Bullet point 1 | 2 | Lilou | Completed | 2021-07-26 | 2021-07-26
Method print && Occur on | Bullet point 2 | 2 | Zhuying | Completed | 2021-07-30 | 2021-07-31
Method Save appointment | Bullet point 3 | 2 | Yipeng Liu | Completed | 2021-07-30 | 2021-07-31
Load file | Bullet point 4 | 2 | Yipeng Liu | Completed | 2021-07-30 | 2021-07-31
Record Keeping | Keeping meeting minutes: https://docs.google.com/document/d/119HChavhPgP2m6X62gWBLtf9sTVJI5TX_w8tMPwsLKM/edit?usp=sharing | 4 | Yipeng Liu | Completed | 2021-07-24 | 2021-08-07
Meeting | Meeting for backend functionality (level 2) | 1 | All | Completed | 2021-07-31 | 2021-07-31 | 07/31 PT 18:00
GUI Calendar Clicking | Level 3 requirement | 3 | All | Waiting
GUI Button Adding 1 | Add the button for Adding and deleting | 1 | Zhuying | Completed | 2021-08-07 | 2021-08-07
GUI Button Adding 2 | Add the Button for read and write file | 2 | Yipeng Liu | Completed | 2021-08-05 | 2021-08-07
GUI Button Adding 3 | Setting the View appointment display | 2 | Lilou | Completed | 2021-08-02 | 2021-08-06
GUI Drawing Update | https://docs.google.com/drawings/d/1wMJD7mv8qKfTTJex7XWlD3nzXKY8igtr7o4MIXpLlf8/edit?usp=sharing | 4 | All | In Progress | 2021-07-31
Schedule meeting with teacher | Wait until GUI is completed | 3 | All | Not Started |  |  | 08/08 PT 16:00

## Utils (hidden)
Priority | Status | Member | All | Lilou | Yipeng Liu | Zhuying
1 | Waiting
2 | Not Started
3 | In Progress
4 | Completed